## Lines of Effort Tracker
NZALC HQ Lines of Effort Tracker
ACTIVE LINES OF EFFORT |  | CRITICAL | IMPORTANT | ROUTINE | STALE (14+ DAYS)
24 |  | 8 | 8 | 8 | 0
Priority | Line of Effort | End State / Output | Progress % | Next Action | Notes | Last Updated
Important | Junior Officer Leadership Training | Lead Leaders formally endorsed through AITC | 10% | Confirm direction with the boss, then draft the 1–2 page proposition for early Sep AITC |  | 2026-08-27
Critical | Combat Mindset Submission |  | 100% |  |  | 2026-08-27
Critical | Pacific Response Group (12 - 13 Aug 26) | Activity delivered and post-activity actions closed | 98% | Submit Storyboard to LCC through ACS |  | 2026-08-27
Critical | Lead Systems Adventure Race (7 - 14 Aug 26) | Race delivered and post-course actions closed | 98% | Submit Storyboard to LCC through ACS |  | 2026-08-27
Critical | Lead Systems, Alpine Tour (24 - 30 Aug 26) | Tour delivered and post-course actions closed | 80% |  |  | 2026-08-27
Critical | NZDF COTY Submission |  | 100% |  |  | 2026-08-27
Critical | Request for Secondary Employment |  | 100% |  |  | 2026-08-27
Critical | NZALC ORBAT | ORBAT confirmed, with contingency options for 2027 established | 50% | Establish contingency options for 2027 | Jim - Retirement Kate - Maternity James - Family | 2026-08-27
Important | 2 CDO COMD ELDA | ELDA delivered to 2 CDO and closed out | 20% | Awaiting feedback from 2 CDO HQ | 16-23 Mar 27 (potential dates) 1-pager submitted | 2026-08-27
Important | 2/1 Leadership Integration Series | All phases of the series delivered | 70% | Ph 3 Nov | Ph 2 complete | 2026-08-27
Important | FY Summary Production Process | Production process documented as a written SOP | 100% |  |  | 2026-08-27
Important | ATG Professional Development | Attendance completed | 100% |  |  | 2026-08-27
Important | 2ER COMD ELDA | ELDA delivered to 2ER and closed out | 10% | 15 pax, LPR and Rocket Model (2x Instr) | 16 Nov (pm) LPR 17 Nov (am) Rocket Model | 2026-09-07
Important | TFCC Course Correction & TF Instructor Transition | Erroneous RF course requirement removed and TF instructor delivery in place | 40% | Call Billy Vince to remove the RF course requirement |  | 2026-08-27
Important | Alpine Touring Resource Review | Resource model decided — reduced internal footprint, contractor support, or course ceased | 5% | Conduct the resource review with Tony |  | 2026-08-27
Routine | NZALC Strategic Planning Tool | Planning tool developed and in use | 0% |  |  | 2026-08-27
Routine | Clothing Cards |  | 100% |  |  | 2026-08-27
Routine | Anaphalaxis Submission | Command decision received and actioned | 100% |  |  | 2026-08-27
Routine | Budget Builder | FY26/27 budget model confirmed and issued | 100% |  |  | 2026-08-27
Routine | NZALC Operating Manual | Manual approved, published and in use | 100% |  |  | 2026-08-27
Routine | Course Nomination & Preparation SOP | SOP approved and implemented | 100% |  |  | 2026-08-27
Routine | ELDA Comd Review | Review completed and reported | 100% |  |  | 2026-08-27
Routine | Support to HUMINT Platoon FTX | Support delivered to FTX | 100% |  |  | 2026-08-27
Critical | 1 CSR Support Session (11 Oct 26) | Session delivered with 360-focused instructor support | 0% | Calendar the session and allocate one — preferably two — instructors |  | 2026-08-27