## Slide 1
NZ Army Leadership Centre
Cost centre 43311
July 2026 against budget
Month 1 of FY26/27. Source: SAP financial management report 43311, July 26, and the NZALC FY26/27 Budget Summary.
FY26/27 MONTH 1 BUDGET ANALYSIS
JULY 2026 | PAGE 1 OF 2
SAP JULY BUDGET
$23,015
phased, no courses in July
JULY ACTUAL
$40,535
176% of the phased budget
VARIANCE
-$17,520
adverse
OF THE ANNUAL PLAN
5.0%
a straight twelfth is 8.3%
THE FINDING
July delivered no training. The first activity of the year, Ser 01 LSYS NCO Advanced, begins in August. The phased budget recognises this: July carries 2.8 per cent of the annual plan, well under a straight twelfth. Actual spend was 5.0 per cent of the annual plan, so the centre consumed roughly two months of budget in a month with no course output.
JULY VARIANCE BY COST ELEMENT
Budget less actual. Bars left of the datum are overspends. The right-hand columns show the full year plan and the share of it already spent in month one; a straight twelfth would be 8 per cent.

## Slide 2
NZ Army Leadership Centre
Cost centre 43311
The year, and what July implies
Reconciliation of the SAP full year plan to the NZALC budget, the exposures July has surfaced, and what needs a decision.
FY26/27 MONTH 1 BUDGET ANALYSIS
JULY 2026 | PAGE 2 OF 2
RECONCILIATION — THE TWO PLANS AGREE
The two plans differ by $50,151. The $50,000 Winsborough uplift accounts for almost all of it, loaded correctly to CE 7290 Professional Fees, which carries $56,551 in SAP against $6,350 in the budget. The rest is line reallocation, chiefly travel down $3,770 offset by training fees up $3,414. Note that the budget summary is internally inconsistent by $150: its cover states variable costs of $502,584, its cost element table $502,434. Against the cover figure the two plans reconcile to $1.
THREE EXPOSURES JULY HAS SURFACED
Spending against cost elements with no budget
$6,065
Civilian overtime $2,847 and sundry expenses $3,217 were incurred against lines that carry zero for the year. These are not phasing differences; there is no budget behind them at any point in FY26/27. If they continue at anything like July's rate the annual exposure is material.
Annual lines largely consumed in month 1
$6,949
Civilian allowances at 53 per cent of the annual line, computer hardware at 58 per cent and vehicle licences at 41 per cent. Some of this is legitimately front-loaded, licences and hardware are typically annual purchases, but civilian allowances at over half the year in month one is a run-rate question, not a timing one.
The forecast is arithmetic, not judgement
$17,521
The full year forecast outturn of $829,147 is simply the July variance added to the remaining phased budget. It assumes every future month lands exactly on plan. It is not a re-forecast and should not be read as one.
WHAT NEEDS A DECISION
1
Establish where overtime and sundry spend belongs
Either a budget line is created for CE 6020 and CE 7395, or the spend is reallocated to the cost elements that should carry it. Running a year against zero-budget lines will distort every month's variance from here.
2
Confirm whether the civilian allowance rate is correct
At July's rate the $5,260 annual line is exhausted by September. Either the rate is wrong or the budget is.
3
Populate the report narrative
The activities conducted, risks, reprioritisation account and CO's comment fields are all blank, and there is no commentary against any variance. A month 1 report with a 76 per cent overspend and no explanation invites the wrong questions.
4
Re-forecast after the first courses complete
August and September carry seven activities. Actual course costs against the per-course budget will be the first real test of the variable-cost assumptions, and the point at which a genuine re-forecast becomes possible.